## Cutover Checklist
Phase | Step ID | Step | Details / Checks | Evidence Required | Owner | Due Date | Status | Notes
Phase 0 — Unit of success | 0.1 | Confirm first live pay date + last legacy pay date | Identify the first pay period that will be processed live in the new provider. Identify whether the first live period includes special cases (year-end, quarter-end, benefits changes, scheduled bonus, etc.). Decide whether you will run one parallel pay period or more than one.
Phase 0 — Unit of success | 0.2 | Lock the validation scope (what you will prove) | Define the outcomes the cutover validation must protect: • Employee outcome: net pay is correct and received on time • Compliance outcome: taxes/statutory items calculate correctly by jurisdiction • Deductions outcome: benefits/other deductions withheld correctly; pre-tax vs post-tax treated correctly • Finance outcome: expense + liabilities outputs stable enough to support close • Operational outcome: payroll can run with defined approvals, deadlines, exception handling
Phase 0 — Unit of success | 0.3 | Define must-match vs allowed variance rules | Create rules before testing so you are not negotiating on launch week. Minimum recommended must-match list: • Net pay by employee • Total taxes withheld by employee (within rounding tolerance) • Employer tax totals by jurisdiction (within rounding tolerance) • Deduction totals by employee by deduction type (for active deductions) • Total funding requirement Allowed variance must be documented. Examples: • Rounding differences within stated tolerance • Accrual timing differences if accounting policy differs • Reporting presentation differences that don’t change underlying amounts
Phase 0 — Unit of success | 0.4 | Decide what “ready” means (go/no-go gates) | Define readiness as explicit evidence-based gates (use the Go/No-Go criteria in this guide).
Phase 1 — Prerequisites | 1.1 | Data completeness check (employee master data) | Verify for the test population (ideally all employees) that the new system has: • Legal name, address, work location • Tax jurisdictions + withholding elections • Pay rate + pay type (hourly/salary) • Pay schedule + pay group assignment • Bank distribution for direct deposit (if applicable) • Benefit elections + deduction codes (if applicable) • Garnishment details (if applicable) • Special earning types (commission, stipend, reimbursements rules) | • Export/report from new system showing fields for test employees • Missing/exception list with owners + due dates
Phase 1 — Prerequisites | 1.2 | Earnings + time input readiness | Confirm how the new payroll will receive earnings: • Timekeeping integration / file import / manual entry / hybrid • Approval path + deadlines for hours, OT, PTO, commissions, bonuses • Cutoff times + who owns late corrections | • Documented payroll calendar for the test period (cutoff, approvals, submission) • Proof that time/earnings for test employees can be entered exactly as legacy inputs
Phase 1 — Prerequisites | 1.3 | Tax setup readiness | Confirm: • All relevant state/local jurisdictions are active for test employees • Reciprocity rules (where relevant) are applied correctly • Special tax scenarios are known (local taxes, multiple work locations) | • Tax jurisdiction report for test employees • Checklist of jurisdictions verified + by whom
Phase 1 — Prerequisites | 1.4 | Benefits + deduction readiness | Confirm: • Deduction codes exist for each benefit • Pre-tax vs post-tax treatment is correct • Employer contribution logic is correct (if reflected in outputs) • Mid-period changes are understood (how treated in each system) | • Deduction setup report + benefit mapping for test employees • Deduction validation plan (which deductions must match exactly)
Phase 1 — Prerequisites | 1.5 | Banking readiness | Confirm: • Bank account info entry is complete • Prenote/testing method (if used) is scheduled • Funding process is defined (who funds, when, approvals) | • Documented funding workflow (owner, timing, approvals) • Confirmation of bank file generation steps + access controls
Phase 1 — Prerequisites | 1.6 | Finance output readiness (minimum viable continuity) | Confirm: • Payroll summaries by earnings, taxes, deductions are available • Payroll register with employee detail is available • A report exists to support journal entry process (even if manual) | • Example reports from new system for the test population • Mapping notes for how payroll categories land in accounting entries
Phase 2 — Design parallel run | 2.1 | Choose the parallel pay period(s) | Use a representative period (not “clean”). Good candidates: • Normal cycle with standard hours + a few exceptions • Cycle that includes benefit deductions • If variable pay exists, cycle with some variable earnings Avoid: • Holiday-shortened/unusual period unless it matches upcoming go-live • Period with radical known data changes (unless unavoidable)
Phase 2 — Design parallel run | 2.2 | Select representative test population | At minimum include: • 5–10 “simple” employees (clean salary or clean hourly) • 5–10 “complex” employees (OT, multi-state, variable pay, benefit tiers, garnishments) • At least one employee for each pay group/schedule if multiple If <25 employees, test population should be most employees. | • List of test employees and why selected (what rule they validate)
Phase 2 — Design parallel run | 2.3 | Decide the comparison level (layers) | Parallel validation layers: • Layer 1 — totals (baseline math) • Layer 2 — employee-level net + taxes (distribution) • Layer 3 — element-level earnings/deductions (mapping + treatment) | • Scoreboard template that supports all three layers
Phase 2 — Design parallel run | 2.4 | Create a discrepancy workflow | Define: • Where discrepancies are logged • How they are classified • Who owns each discrepancy type • SLA for resolution (e.g., 48 hours for must-match blockers) | • Discrepancy log template + owners assigned
Phase 3 — Execute parallel run | 3.1 | Run legacy payroll as normal | Treat the legacy run as the known output for the period. | • Legacy payroll register • Legacy payroll summary (taxes, deductions, employer costs if available) • Legacy funding totals
Phase 3 — Execute parallel run | 3.2 | Run new payroll using the same inputs | Use identical hours, earnings events, and deduction elections as legacy. | • New payroll register • New payroll summary reports • New funding totals
Phase 3 — Execute parallel run | 3.3 | Populate the Parallel Run Scoreboard | Use the structured comparisons (totals → employee → element). Do not eyeball it.
Phase 3 — Execute parallel run | 3.4 | Investigate differences using classification rules | Classify differences: • Must match (go/no-go blocker until resolved) • Allowed with explanation (documented) • Unknown (requires root cause) | • Updated discrepancy log with root cause notes + resolution status
Phase 3 — Execute parallel run | 3.5 | Re-run if needed | If must-match items exist, do not proceed. Re-run only after: • Config/data fixes applied • You can explain why rerun should change results • Owners agree rerun isn’t masking unresolved issues
Phase 4 — Go-live readiness | 4.1 | Complete Go/No-Go criteria | Use the Go/No-Go section as evidence-based sign-off.
Phase 4 — Go-live readiness | 4.2 | Lock configuration changes | After final parallel run, restrict changes. Emergency changes require documented approval + re-validation of impacted items. | • Simple change log (what changed, why, who approved, what was re-tested)
Phase 4 — Go-live readiness | 4.3 | Prepare first live cycle controls | Schedule first-cycle controls so go-live doesn’t become a long stabilization. | • First-cycle control checklist (later in guide under Migration considerations)

## Scoreboard - Totals
Metric ID | Metric | Legacy Total | New Total | Difference | Status (Must match / Allowed / Unknown) | Notes / Root cause
A1 | Total gross wages (all employees, all earnings)
A2 | Total net pay (all employees)
A3 | Total employee taxes withheld
A4 | Total employer taxes
A5 | Total deductions withheld (benefits + other deductions)
A6 | Total funding required (if applicable)

## Scoreboard - Employees
Employee name / ID | Net pay (Legacy) | Net pay (New) | Taxes withheld (Legacy) | Taxes withheld (New) | Deductions total (Legacy) | Deductions total (New) | Status (Must match / Allowed / Unknown) | Notes / Root cause

## Scoreboard - Element
Employee name / ID | Type (Earnings/Deduction/Tax) | Element / Code | Legacy Amount | New Amount | Difference | Status (Blocker/Allowed/Unknown) | Notes / Root cause

## Go-NoGo Criteria
Section | Requirement | Evidence / Notes | Owner | Status
Go criteria | Parallel run completed with evidence pack | Scoreboard populated (totals + employee-level + element-level for complex cases) Discrepancy log closed for all must-match items Allowed variances documented and approved
Go criteria | Banking process validated | Bank file generation method confirmed Funding workflow documented Access controls and approvals defined If prenote/testing is used, executed per bank process
Go criteria | Taxes and deductions verified for test population | Jurisdictions verified for each multi-state/local case Benefit deductions match expected treatment (pre-tax/post-tax) Garnishments validated or explicitly deferred with documented risk decision
Go criteria | Operational calendar locked for first live payroll | Cutoff dates and approvals published Owners assigned for time/earnings, payroll run, funding, and exceptions Escalation path defined for late changes
Go criteria | First-cycle controls scheduled | Post-run audit step planned for first live cycle Second-person review exists for bank totals and exception handling First live cycle issue log exists with owners and SLAs
No-go trigger | Any test employee net pay mismatch without root cause
No-go trigger | Any tax jurisdiction applied incorrectly in new system for test employees
No-go trigger | Any high-impact deduction mismatch (benefits/garnishments) without decision and evidence
No-go trigger | Banking workflow not validated or unclear funding ownership
No-go trigger | Material discrepancies in totals not classified and explained

## Sign-off Block
Prepared by (name / role) | Date
Reviewed by (name / role) | Date
Approved by (name / role) | Date